## Slide 1: What I am doing
Create background radiation simulations for the Phase 1 detector
Click HERE

## Slide 2: 4/11/17
DONE
Installed Personal BACCARAT
Got Macro from Ryan
Looked for vessel dimensions
TO DO
Permission to access files?
Include geometry files in macro
Install DAWN visualization? (optional?)
Get macro checked
Run macro

## Slide 3: 4/18/17
  DONE
  Found (hopefully) the files for the dimensions of the vessels
  Edited the macro to include them
  Edited farmoutBACCARAT.sh to use the macro
  Started Linux tutorial
TO DO
Transfer the macro to the server
Run a test macro (small sample size)
If errors arise, edit macro until it works
Run the macro (large sample size)

## Slide 4: 4/25/17
  DONE
  Finished Linux tutorial
  Fixed some issues with running the macro (but ran into some more)
TO DO
Fix output file problems
Run a test macro (small sample size)
If errors arise, edit macro until it works
Run the macro (large sample size)

## Slide 5: SPRING 2017 Semester Summary What I have Learned
How the LZ Experiment works and the basic geometries of the detectors
  Does not have much outside use, but it will certainly help with understanding for understanding results (once I get them)
Basic knowledge on using Linux and writing macros
  Both will be very useful for the summer, where I will be doing much of what I am doing now, and useful to know in general
Seeking Help
  I ran into many walls, so I had to find ways to keep productive while I was stuck in some area

## Slide 6: Summer Goals
Finally run the macro, and make necessary edits
Be able to interpret my results
Write more macros (hopefully with visualization)
Do more tests with other components of the detector vessel
Move on to other simulations

## Slide 7: 5/23/17
  DONE
  Fixed server issues
  Fixed file permission issues
  Ran first successful job (yet to get results)
TO DO
Edit macro until I get results that I want
Display results (histogram)
Run the macro with larger sample size
Be able to explain results and effect on experiment