## Slide 1: Accelerator R&D : MuCollider Priorities and Plans
Princeton Workshop Discussion
Feb 23, 2024
K.Amm, S.Belomestnykh, S.Berg, C.Bhat, S.Cousineau, N.Evans, S.Gourlay, A.Hoover, T.Luo, V.Morozov, M.Palmer, V.Shiltsev, D.Stratakis, A.Valishev, K.Yonehara, et al

## Slide 2: High Level Priorities (from Day 1)
Demonstrator design
Strengthen Physics case (Theory-Exp)
Resurrect Accelerator expertise
10 pCM MuColl design with IMCC
(did I miss smth?)

## Slide 3: Targetry R&D (proto)Plan
 | Yr 1 | Yr 3 | Yr 5
Simulation codes | Univ. in AI Implement beam irradiation model | Cont’d | Cont’d Validate simulation
Material R&D | Collaborate RaDIATE Identify MuC specific | Cont’d Beam irradiation + PIE | Cont’d Preliminary design
Relevant beam/no beam tests | LDRD FNAL, US-Japan GARD HPT R&D Plan at SNS 2nd TGT for MuC target | Cont’d R&D at SNS 2nd TGT for MuC target | Cont’d
Capture system design | Simulate solenoid, horn, FODO | Cont’d | Down selection
Design Demonstrator target | Simulate IMCC type target & Evaluate other possible solution | Cont’d | Down selection
Collider Design: target | Collaborate IMCC | Collaborate IMCC | Collaborate IMCC
Synergies | Neutrino target, Low energy muon target, | Neutrino target, Low energy muon target, | Neutrino target, Low energy muon target, SNS

## Slide 4: Magnet R&D (proto)Plan
 | Yr 1 | Yr 3 | Yr 5
Solenoid design/prototyping for late 6D Cooling Stage parameters | Evaluate solenoid parameters, stress levels, and engineering constraints. | Deliver an R&D prototype magnet design ready for construction. | Integrate solenoid test results into MC late 6D cell prototype.
Solenoid quench protection requirements (late 6D, Final) | Preliminary stored energy and coil-to-coil coupling requirements | Deliver a quench system conceptual design (6D) | Integrate 6D quench system results into MC late 6D cell prototype.
Late 6D cryomodule (RF+magnet) design | ? | Conceptual Design | Technical design ready for prototyping
Final cooling solenoid | ? | Conceptual Design for 40-50T prototype | R&D to support 40-50T prototype
Design Demonstrator magnets | Based on performance requirements specify suitable Demonstrator (RF+magnet) stage. | Demonstrator Conceptual Design | Demonstrator Technical Design and Construction Proposal
Accelerator Design: Fast Ramping Magnets | Explore limits of peak field | Fast Ramping Magnet Conceptual Design | Technical Design for Fast Ramp Magnet+PS demonstration
Collider Design: magnets | Explore radiation shielding and combined function design options. | Conceptual Design of MC Dipole (Nb3Sn, HTS). Identify detailed cable and magnet R&D program required | Technical Design of MC Dipole (perhaps initially Nb3Sn version only with HTS to follow). Continue HTS conductor studies.
Synergies | MDP, 40T NHFML design study, Compact fusion |  | 

## Slide 5: RF R&D (proto)Plan
 | Yr 1 | Yr 3 | Yr 5
1.5 cell Demonstrator RF | RF design of the 704 (?) MHz cavity | RF and engineering design, with system integration considerations | Hardware: key components prototyping
NCRF Breakdown study in strong B field | Study the breakdown physics and the mitigation methods by analysis and simulation | Explore testing opportunities with existing facilities and make testing plans, and explore possibility of building a dedicated facility | Summarize the first testing results and provide input to Demonstrator design
SRF development | Initiate collaboration with CERN on Nb/Cu | Develop SRF cavity concepts | Prototype and test SRF cavities, demonstrate MC specs
Design Demonstrator RF | Initial concept of RF for demonstrator | Demonstrator RF concept | Final design of Demonstrator RF
Collider Design: RF | Initiate studies of beam-cavity interactions | Provide input for SRF cavity concepts | Develop RF system concepts
Synergies | GARD, FCC-ee, C3, IMCC | GARD, FCC-ee, IMCC | IMCC

## Slide 6: Muon Cooling R&D (proto)Plan
 | Yr 1 | Yr 3 | Yr 5
Solenoid Prototyping | Design First Solenoid with Dipole Field | Build first solenoid. Design of demonstrator solenoid(s). Design prototype magnet package. | Build second solenoid for gradient testing. Build solenoids for prototype
RF Cavity Prototyping | Design RF cavities for prototype and gradient tests. Power supply design. | Design RF cavity for Demonstrator. Build gradient test cavity. | Begin gradient testing program. Build cavity for prototype.
Physics Design | Design of demonstrator cooling cell | Finalize prototype cell design | ? Contribution to the Demonstrator Design
Engineering | Demonstrator cooling channel. Gradient test module. | Prototype cell. | Technical design of the Demonstrator complete
Synergies | IMCC | IMCC | IMCC

## Slide 7: Proton Driver R&D (proto)Plan
 | Yr 1 | Yr 3 | Yr 5
Injection/painting | SNS exp’t: design? | SNS exp’t: hardware design | Inj/painting studies PIP-II
Bunch compression & beam dynamics studies; beam halo collimation | SNS exp’t: design? // SC studies at FNAL Booster, SC IOTA studies | SNS exp’t: hardw.// SC studies at FNAL Booster; SC IOTA studies | SNS exp shows ~10^14 compressed in 20-30 ns; SC IOTA studies
Stripping | Design of LACE system at SNS | Constr. of LACE system at SNS | Demonstrate LACE system at SNS
Benchmark models | modeling via GARD ? IOTA… | vs results of studies to date | vs results of studies to date
Design Demonstrator: Proton Beam | Where? FNAL? Decide… | Join forces with FNAL ACE WG | Proton beamline and infrastructure design
Collider Design: PD | Contribute to IMCC PD; Coordinate with ACE-TF | Contribute to IMCC PD; Coordinate with ACE-TF | Contribute to IMCC PD; Coordinate with ACE-TF
Synergies | ACE-BR, SNS, ?, IMCC, future AMF, IOTA | ACE-BR, SNS, ?, IMCC, future AMF, IOTA | ACE-BR, SNS, ?, IMCC, future AMF, IOTA